## Sheet1
Logbook - project Race car |  |  |  |  | Name: Jurijs Z.(440882), Karolis J.(517546),Tarik M.(523830)
Company: ACEcar |  |  |  |  | Dmytro T.(516824), Miguel P.M.(524262) |  |  |  |  | Legenda
Legnda - A, B, J | [9 empty] | Code | Location
The locations and corresponding code can be found in the legenda | [9 empty] | A | Personal residence
| Week | 1 | [6 empty] | total time | B | W2.40 -Saxion
Work done | Date | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | x | C | W2.29a - Saxion
Lecture |  | 2022-02-07: 0.45; 2022-02-11: 3.15 | 3.6 | D | W2.30a - Saxion
Problem definition | [8 empty] | 1 | E | W2.30b - Saxion | bar: 2022-02-11
Project plan |  | 2022-02-11: 0.5; 2022-02-12: 1; 2022-02-13: 2 | 3.5 | F | OTSWO - Saxion
Quality | [8 empty] | 1 | G | W3.47 - Saxion | bar: 2022-02-13
Risk assesment | [8 empty] | 1 | H | W2.42 - Saxion | bar: 2022-02-12
General planning | [8 empty] | 1 | I | W2.43 - Saxion | bar: 2022-02-13
Personal planning | [8 empty] | 1 | J | FabLab | bar: 2022-02-11
Meeting |  | 2022-02-11: 0.5 | 0.5 | # hr | Hours spend
Prepare meeting |  | 2022-02-11: 0.5 | 0.5
|  | 2022-02-12: Subtotal | 13.1
| Week | 2022-02-07: 2 | total time
Work done | Date | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | x
Meeting |  | 2022-02-18: 0.5; 2022-02-20: 0.5 | 1
Project plan | [8 empty] | 3 | bar: 2022-02-18 to 2022-02-20
Risk assesment | [8 empty] | 2 | bar: 2022-02-17; 2022-02-19
quality | [8 empty] | 2 | bar: 2022-02-18; 2022-02-20
Lecture |  | 2022-02-14: 0.45; 2022-02-18: 3.15 | 3.6
Logbook |  | 2022-02-19: 0.1 | 0.1
Prepare meeting | [8 empty] | 2 | bar: 2022-02-15; 2022-02-18
|  | 2022-02-19: Subtotal | 13.7
|  | 2022-02-19: Accumulative total | 26.8
| Week | 2022-02-14: 3 | total time
Work done | Date | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | x
Functional design |  |  | 1 |  | 1 | 3 | 1 | 1 | 7
Measurement plan | [8 empty] | 2 | bar: 2022-03-01; 2022-03-05
Measurement plan research |  | 2022-03-01: 1; 2022-03-06: 3 | 4
|  | 2022-03-05: subtotal | 13
|  | 2022-03-05: accumulative total | 39.8
| Week | 2022-02-28: 4 | total time
Work done | Date | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | x
Lecture |  | 2022-03-08: 0.45; 2022-03-11: 3.15 | 3.6
Prepare meeting |  | 2022-03-12: 0.5 | 0.5
Meeting | [8 empty] | 1 | bar: 2022-03-12
Doing measurements | [8 empty] | 1 | bar: 2022-03-11
Processing measurements |  | 2022-03-12: 0.5 | 0.5
Tests research |  | 2022-03-10: 1; 2022-03-13: 2 | 3
Physical measurements machine | [8 empty] | 2 | bar: 2022-03-10; 2022-03-12
Functional design plan | [8 empty] | 2 | bar: 2022-03-10; 2022-03-13
Finalize functional design | [8 empty] | 3 | bar: 2022-03-11 to 2022-03-13
|  | 2022-03-12: Subtotal | 16.6
|  | 2022-03-12: Accumulative total | 56.4
| Week | 2022-03-07: 5 | total time
Work done | Date | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | x
Lecture |  | 2022-03-15: 0.45; 2022-03-18: 3.15 | 3.6
Prepare meeting |  | 2022-03-18: 0.5 | 0.5
improve functional design | [8 empty] | 1 | bar: 2022-03-15
Adapt functional design |  | 2022-03-16: 1; 2022-03-18: 0.1 | 1.1
Go/No Go meeting |  | 2022-03-18: 0.1 | 0.1
Prepare Go/No go | [8 empty] | 2 | bar: 2022-03-17 to 2022-03-18
Technical design research | [8 empty] | 3 | bar: 2022-03-17; 2022-03-19 to 2022-03-20
Technical design discussion | [8 empty] | 2 | bar: 2022-03-19 to 2022-03-20
|  | 2022-03-19: Subtotal | 13.3
|  | 2022-03-19: accumulative total | 69.7
| Week | 2022-03-14: 6 | total time
Work done | Date | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | x
Lecture |  | 2022-03-22: 0.45; 2022-03-25: 3.15 | 3.6
prepare meeting |  | 2022-03-24: 0.5 | 0.5
Mechanical design | [8 empty] | 1 | bar: 2022-03-26
Set up TAR | [8 empty] | 1 | bar: 2022-03-24
Meeting | [8 empty] | 3 | bar: 2022-03-22; 2022-03-26 to 2022-03-27
3D scan coffeemachine | [8 empty] | 6 | bar: 2022-03-22 to 2022-03-27
Finish TD | [8 empty] | 4 | bar: 2022-03-22; 2022-03-25 to 2022-03-27
|  | 2022-03-26: Subtotal | 19.1
|  | 2022-03-26: accumulative total | 88.8
| Week | 2022-03-21: 7 | total time
Work done | Date | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | x | Legenda
Prepare meeting |  | 2022-04-01: 0.5 | 0.5 | Code | Location
Meeting | [8 empty] | 1 | A | Personal residence | bar: 2022-04-01
Polish mechanical design | [8 empty] | 2 | B | W2.40 -Saxion | bar: 2022-03-31 to 2022-04-01
Assist in PCB design | [8 empty] | 3 | C | W2.29a - Saxion | bar: 2022-03-31; 2022-04-02 to 2022-04-03
Component selection | [8 empty] | 2 | D | W2.30a - Saxion | bar: 2022-03-29; 2022-04-01
Fablab preparation |  | 2022-03-31: 1; 2022-04-01: 2; 2022-04-02: 1; 2022-04-03: 1 | 5 | E | W2.30b - Saxion
[9 empty] | 0 | F | OTSWO - Saxion
|  | 2022-04-02: Subtotal | 13.5 | G | W3.47 - Saxion
|  | 2022-04-02: accumulative total | 102.3 | H | W2.42 - Saxion
[10 empty] | I | W2.43 - Saxion
[10 empty] | J | FabLab
[10 empty] | # hr | Hours spend
| Week | 2022-03-28: 8 | total time
Work done | Date | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | x
Prepare meeting |  | 2022-04-05: 0.5; 2022-04-08: 0.5 | 1
Meeting |  | 2022-04-05: 1; 2022-04-08: 2 | 3
Prepare PCB print | [8 empty] | 3 | bar: 2022-04-06 to 2022-04-08
Prepare laser cutting | [8 empty] | 1 | bar: 2022-04-07
Laser cutting | [8 empty] | 2 | bar: 2022-04-05; 2022-04-09
Assist in pcb design | [8 empty] | 1 | bar: 2022-04-08
|  | 2022-04-09: Subtotal | 11
|  | 2022-04-09: accumulative total | 113.3
| Week | 2022-04-04: 9 | total time
Work done | Date | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | x
Compose component list | [8 empty] | 2 | bar: 2022-04-26; 2022-04-29
Case design tweaks | [8 empty] | 1 | bar: 2022-04-29
PCB tweaks | [8 empty] | 2 | bar: 2022-04-26; 2022-04-29
PCB Print preparation | [8 empty] | 5 | bar: 2022-04-26; 2022-04-28 to 2022-05-01
PCB Printing | [8 empty] | 1 | bar: 2022-04-29
|  | 2022-04-30: Subtotal | 11
|  | 2022-04-28: 1; 2022-04-30: accumulative total | 113.3
| Week | 2022-04-25: 10 | total time
Work done | Date | [7 empty] | x
Exam week
PCB printing | [8 empty] | x
accumulative total
Legenda
| Week | 2022-04-25: 11 | total time | Code | Location
Work done | Date | [7 empty] | x | A | Personal residence | bar: 2022-04-29
Exam week | [9 empty] | B | W2.40 -Saxion
[10 empty] | C | W2.29a - Saxion
[10 empty] | D | W2.30a - Saxion
[10 empty] | E | W2.30b - Saxion
[10 empty] | F | OTSWO - Saxion
| Week | 2022-04-25: 12 | total time | G | W3.47 - Saxion
Work done | Date | [7 empty] | x | H | W2.42 - Saxion
Holiday | [9 empty] | I | W2.43 - Saxion
[10 empty] | J | FabLab
Prepare meeting | [8 empty] | 1 | # hr | Hours spend | bar: 2022-05-01
|  | 2022-04-30: accumulative total | 1
| week | 2022-04-25: 13 | total time
Work done | Date | 2022-05-09 | 2022-05-10 | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | x
Meeting | [8 empty] | 2 | bar: 2022-05-10; 2022-05-15
Assembly preparations | [8 empty] | 2 | bar: 2022-05-09 to 2022-05-10
Mechanical design revison |  | 2022-05-09: 2; 2022-05-10: 1 | 3
Finalize report template |  | 2022-05-09: 2; 2022-05-15: 1 | 3
Recutting Casing | [8 empty] | 1 | bar: 2022-05-09
Soldering mega shield | [8 empty] | 2 | bar: 2022-05-10 to 2022-05-11
Prepare meeting |  | 2022-05-09: 0.5; 2022-05-10: 1 | 1.5
|  | 2022-05-14: Subtotal | 14.5
|  | 2022-05-14: accumulative total | 128.8
| week | 2022-05-09: 14 | total time
Work done | Date | 2022-05-23 | 2022-05-24 | 2022-05-25 | 2022-05-26 | 2022-05-27 | 2022-05-28 | 2022-05-29 | x
Meeting | [8 empty] | 2 | bar: 2022-05-23 to 2022-05-24
Lecture |  | 2022-05-24: 3 | 3
Performance testing |  | 2022-05-23: 2; 2022-05-24: 1 | 3
Finalize report |  | 2022-05-23: 2; 2022-05-24: 1 | 3
Regression testing |  | 2022-05-23: 2; 2022-05-24: 1 | 3
Acceptance testing |  | 2022-05-23: 2 | 2
Main system report |  | 2022-05-23: 2 | 2
|  | 2022-05-28: Subtotal | 18
|  | 2022-05-28: accumulative total | 146.8